## Roadmap
Project Goal: This project aims to predict the outcomes of football matches (Win/Draw/Loss) by leveraging detailed individual player performance data.
Milestone | Outcomes | Success Metric: | Timeframe | August | September
1. Data Foundation | A clean aggregated dataset ready for feature engineering | Completion of EDA notebook and a final aggregated_matches.csv file. | August - September
2. Feature Engineering | A final dataset enriched with predictive features like team form. | A final_model_data.csv file ready for the modeling phase. | September
3. Modeling & Evaluation | A trained evaluated and saved classification model. | A final .pkl model file with an accuracy score that beats the baseline. | September
4. Interactive App Development | A functional web application that serves live predictions from the model. | A working app.py script that correctly predicts match outcomes based on user input. | September
5. Finalization & Documentation | A complete well-documented and professional project repository. | A polished GitHub repository with a comprehensive README.md file. | September

## Gantt chart
[7 empty] | AUGUST |  |  |  | S E P T E M B E R
Ref | Milestones/Tasks | Start Date | End Date | Duration (days) | Team | Dependencies | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | 1.1,Load & Inspect Raw Data | 2025-08-28 | 2025-08-28 | 1 | Data Lead | Milestone | bar: AUGUST 28
| 1.2,Clean Data (Handle NaNs, Correct Types) | 2025-08-29 | 2025-08-30 | 2 | Data Lead | 1.1 | bar: AUGUST 29 to AUGUST 30
| 1.3,Aggregate Player Stats to Match-Level | 2025-08-31 | 2025-09-02 | 3 | Data Lead | 1.2 | bar: AUGUST 31 to S E P T E M B E R 2
| 1.4,Exploratory Data Analysis (EDA) & Visualization | 2025-09-03 | 2025-09-05 | 3 | Data Lead | bar: S E P T E M B E R 3 to S E P T E M B E R 5
2 | [5 empty] | Milestone
3 | [5 empty] | Milestone
4 | [5 empty] | Milestone
5 | [5 empty] | Milestone
6 | [5 empty] | Milestone

## Schedule
Ref | Milestones/Tasks | Start Date | End Date | Duration (days) | Team | Dependencies
1.1 | Load & Inspect Raw Data | 2025-08-28 | 2025-08-28 | 1 | Data Lead
1.2 | Clean Data (Handle NaNs Correct Types) | 2025-08-29 | 2025-08-30 | 2 | Data Lead | 1.1
1.3 | Aggregate Player Stats to Match-Level | 2025-08-31 | 2025-09-02 | 3 | Data Lead | 1.2
1.4 | Exploratory Data Analysis (EDA) & Visualization | 2025-09-03 | 2025-09-05 | 3 | Data Lead | 1.3
2.1 | Engineer "Team Form" (Rolling Averages) | 2025-09-06 | 2025-09-08 | 3 | Data Lead | 1.4
2.2 | Final Feature Selection & Prep | 2025-09-09 | 2025-09-09 | 1 | Data Lead | 2.1
2.3 | Encode Categorical & Scale Numerical Data | 2025-09-10 | 2025-09-11 | 2 | Data Lead | 2.2
3.1 | Split Data into Training & Testing Sets | 2025-09-12 | 2025-09-12 | 1 | ML Lead | 2.3
3.2 | Train & Evaluate Baseline Model | 2025-09-13 | 2025-09-14 | 2 | ML Lead | 3.1
3.3 | Train & Evaluate Advanced Model | 2025-09-15 | 2025-09-17 | 3 | ML Lead | 3.2
3.4 | Final Model Selection & Save File | 2025-09-18 | 2025-09-20 | 3 | ML Lead | 3.3
4.1 | Set up Streamlit Environment & Basic UI | 2025-09-21 | 2025-09-21 | 1 | Dev Lead | 3.4
4.2 | Load Model & Write Prediction Logic | 2025-09-22 | 2025-09-23 | 2 | Dev Lead | 4.1
4.3 | Refine UI and Test App Functionality | 2025-09-24 | 2025-09-25 | 2 | Dev Lead | 4.2
5.1 | Clean & Comment All Code and Notebooks | 2025-09-26 | 2025-09-27 | 2 | Project Lead | 4.3
5.2 | Update README.md with Results & Instructions | 2025-09-28 | 2025-09-29 | 2 | Project Lead | 5.1
5.3 | Final Review & Polish GitHub Repo | 2025-09-30 | 2025-09-30 | 1 | Project Lead | 5.2